ORANGE BOARD OF EDUCATION   					                        		2014-2015

PROPOSED BUDGET PROCESS CALENDAR

SUBJECT TO CHANGE

| October 15, 2013 | PCL Meeting: - Business Office notified Principals that the School Based Budget Excel Worksheet and FTE list is available on the budget (X) Network Directory. FTE list verification should commence, with updates, feedbacks and comments to be completed by 10/31/2013. |
| --- | --- |
| November 1, 2013 | Supervisor’s Meeting: - Business Office and Cabinet will discuss budget strategies, protocols, and efficiencies relating to curriculum and non-curriculum expectations. |
| November 15, 2013 | Finance Committee Budget preparation update meeting ( BA & Supt. will present and obtain budget recommendations) |
| November 19, 2013 10:30 AM | School Based Budget Work Sheet Overview and Training sessions. Principal Meeting/Cabinet Meeting |
| November 19, 2013 | Business Office will provide Maintenance Budget Excel Worksheets for 2014-2015 budgets to Principals & School Leadership Council (SLC). (Worksheet with October 15, ASSA enrollment and projected Non-Salary funds will be placed on District Network Directory X) |
| November 21 2013 Cabinet meeting | Central Office Departmental budget sheets and FTE data will be distributed to Central Office Administrators during cabinet meeting. Cabinet will discuss budget strategies, protocols, efficiencies and curriculum expectations. |
| December 12, 2013 Cabinet meeting | Business Office will provide the revised and updated staff (FTE) sheets for update to cabinet. The revised Budget Position Control Roster) file will be placed in each schools budget folder on District Network Directory X |
| December 19, 2013 Cabinet meeting | Cabinet will discuss updated budget strategies, protocols, and efficiencies curriculum and non-curriculum expectations. District level budget discussions and new initiatives. |
| December 23, 2013 through January 1, 2014 | CHRISTMAS RECESS (District Closed) |
| January 16, 2014 | Central Office Departmental budget sheets and all backup justifications will be returned to Business Office during cabinet meeting. District level budget discussions and new initiatives. |
| January 23, 2014 | Cabinet Budget meeting will be held to discuss budget recommendations. ( Principals face to face meeting schedule will be developed) |
| January 24, 2014 | 2014-2015 School-Based Budget Excel Worksheets will be submitted to Business Office, meaning:- (School Based Budgets Will No Longer Be Available On The X Network Directory By End of this Business Day) |
| February 3,4,5,6 & 7 2014 | Principals face to face budget meeting with cabinet members. |
| February 11, 2014 | 2014-15 Budget update will be presented during Administrative PLC Meeting. |
| February 13, 2014 | Business Office will complete updating School Based Budget Excel worksheet, also complete Central Office Dept. budget with staff and salary data and present an update to cabinet. |
| February 17-21, 2014 | WINTER RECESS (District Closed) |
| February 26, 2014 3:00 PM | Finance Committee Budget update/review meeting ( BA & Supt. will present budget status) |
| February 27, 2014 Special Cabinet Meeting | Final Cabinet budget meeting and School Building Administrators, SLCs and Central Office Administrators will sign-off on School Based Balanced Budgets work-papers |
| February 28, 2014 Special Board Budget Meeting | Finance Committee will present district budget status and recommendations to whole Board and Community during Board meeting. Board approves the submission of a balanced District 2014-2015 Budget. |
| March 5, 2014 | District will Transmit 2014-15 Budget to Department of Education (DOE) |
| March 21, 2014 time TBD | Board of Schools Estimate budget and tax adoption public meeting |